Founder Exit Master Checklist EXOS - Founder's Exit Strategy Operating System ¦ 10-Stage Master Control Checklist

The single source of truth for managing the founder exit journey from initial assessment through post-close transition. This version is aligned to the current EXOS operating architecture: ASSESS → VALUE → IMPROVE → PREPARE → MARKET → QUALIFY → NEGOTIATE → DILIGENCE → CLOSE → TRANSITION.

HOW TO USE THIS MASTER CHECKLIST

Use the checklist as a management control document, not as a rigid linear script. Start at the stage that reflects your current situation.

Assign an owner and due date to every material action. During an active transaction, review open items at least weekly.

Use Folder 00 Executive Command Center and Owner Exit Decision Dashboard to identify priorities and decisions requiring owner attention.

Use the referenced EXOS folders and tools for diagnostics, calculations, AI-assisted analysis, transaction control, and advisor coordination.

Mark a stage complete only when its gate conditions are satisfied or the owner and advisors explicitly accept the remaining risk.

Retain important assumptions, scores, valuation outputs, buyer comparisons, LOI analyses, diligence findings, and closing records for advisor review.

Founder: ______________________________    Company: ______________________________    Target Exit / Close Date: __________________    Lead M&A Advisor: ______________________________

ASSESS — Determine whether the owner and business are genuinely exit-ready.

### Primary EXOS route: 01 — EXIT STRATEGY & OWNER OBJECTIVES; 02 — EARLY EXIT DIAGNOSTICS

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 1 | Clarify owner objectives, timing, personal “enough” number, legacy priorities, and post-exit vision. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 2 | Complete the Executive Exit Readiness Assessment and establish the baseline Exit Readiness Score. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 3 | Complete founder dependency, transferability, management depth, financial quality, revenue quality, concentration, and deal-killer diagnostics. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 4 | Identify personal guarantees, ownership/cap-table issues, legal/compliance issues, key-person risks, and unresolved disputes. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 5 | Decide whether the current strategic direction is SELL, WAIT, IMPROVE, or PREPARE using the Owner Exit Decision Dashboard. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 6 | Create a prioritized risk and remediation list for every ORANGE or RED readiness issue. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 7 | Record the baseline in the Executive Command Center and establish the review cadence. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: owner direction is explicit; baseline is established; material readiness risks are known and owned.

VALUE — Establish defensible enterprise value and seller economics.

### Primary EXOS route: 03 — VALUATION & EXIT ECONOMICS; 06 — EXIT CALCULATOR SUITE

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 8 | Normalize EBITDA and document proposed add-backs with supporting evidence. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 9 | Estimate enterprise value using appropriate valuation approaches and realistic market multiples. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 10 | Calculate the minimum acceptable exit price and owner net-proceeds requirement. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 11 | Model transaction costs, debt payoff, working capital, taxes, and other reductions to proceeds. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 12 | Model all-cash, earnout, rollover equity, seller note, and mixed-consideration structures. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 13 | Calculate risk-adjusted seller value for contingent and deferred consideration. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 14 | Validate material valuation and tax assumptions with qualified professionals. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: valuation range, minimum acceptable outcome, and seller proceeds assumptions are documented and professionally challenged.

IMPROVE — Increase value, transferability, predictability, and buyer confidence before sale.

### Primary EXOS route: 04 — EXIT PLANNING & VALUE CREATION; 05 — VALUE MAXIMIZATION OPERATING SYSTEM

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 15 | Create the 12/24/36-month value-creation roadmap and assign initiative owners. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 16 | Reduce founder dependency by transferring relationships, decisions, knowledge, and operating authority. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 17 | Improve management depth and key-employee retention. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 18 | Reduce customer, supplier, product, channel, and key-person concentration where practical. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 19 | Improve recurring/predictable revenue, margins, financial reporting quality, and KPI discipline. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 20 | Document critical processes, controls, contracts, IP, systems, and operating procedures. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 21 | Track Before vs. After enterprise value, readiness, likely multiple, founder dependency, and other material measures. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 22 | Use the Exit Value Early Warning Monitor to surface deterioration. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: value-creation priorities are executed or intentionally accepted; readiness and transferability show measurable improvement.

PREPARE — Make the company and owner transaction-ready before buyer outreach.

### Primary EXOS route: 08 — EXIT PREPARATION & TRANSACTION READINESS

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 23 | Assemble the exit advisory team: M&A advisor/investment banker, transaction attorney, CPA/tax advisor, QoE firm, wealth advisor, estate attorney, insurance advisor, lender, and valuation professional as needed. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 24 | Complete sell-side QoE or equivalent financial preparation appropriate to the transaction. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 25 | Build and quality-check the virtual data room. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 26 | Prepare the CIM, teaser, management presentation, buyer FAQ, and supporting materials. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 27 | Resolve material legal, financial, tax, operational, HR, IP, insurance, and compliance cleanup items. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 28 | Prepare management for buyer meetings and diligence. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 29 | Complete the Transaction Readiness Dashboard and Stage & Gate review before market launch. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: advisors, materials, data room, financial preparation, and transaction readiness are sufficient to launch.

MARKET — Create a controlled buyer process and competitive tension.

### Primary EXOS route: 09 — BUYER STRATEGY & QUALIFICATION

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 30 | Define strategic, financial, internal, family, ESOP, or other buyer/path categories appropriate to the exit. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 31 | Build and prioritize the buyer universe. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 32 | Establish confidentiality, NDA, information-release, and buyer-contact protocols. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 33 | Launch controlled outreach and track buyer engagement. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 34 | Distribute teaser/CIM materials according to the agreed process. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 35 | Track indications of interest, questions, management-meeting requests, and process milestones. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 36 | Protect business confidentiality and minimize operational disruption during the process. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: buyer outreach is controlled, confidential, and producing a credible qualified buyer set.

QUALIFY — Focus management time on buyers that can actually close and meet owner objectives.

### Primary EXOS route: 09 — BUYER STRATEGY & QUALIFICATION

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 37 | Complete buyer qualification scorecards for serious parties. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 38 | Evaluate strategic fit, financial capacity, decision authority, financing plan, reputation, culture, and transaction history. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 39 | Monitor buyer commitment and closing certainty. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 40 | Compare buyers using the Buyer Ranking Prioritization Matrix. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 41 | Evaluate headline price versus risk-adjusted seller value and non-financial owner priorities. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 42 | Identify red flags, weak financing, unusual conditions, or buyer behavior that could create re-trade risk. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 43 | Select the preferred buyer(s) and preserve credible alternatives until appropriate. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: preferred buyer(s) are selected based on economics, fit, capacity, certainty, and risk—not headline price alone.

NEGOTIATE — Protect seller economics, certainty, control, and acceptable risk.

### Primary EXOS route: 12 — NEGOTIATION, LOI & DEAL STRUCTURE; 07 — AI EXIT INTELLIGENCE; 06 — EXIT CALCULATOR SUITE

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 44 | Compare LOIs across price, cash at close, earnout, rollover, seller note, escrow, indemnity, working capital, financing, exclusivity, and transition obligations. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 45 | Run the Risk-Adjusted Deal Value Calculator for each serious structure. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 46 | Use the Owner Exit Decision Dashboard for ACCEPT / NEGOTIATE / WALK AWAY decisions. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 47 | Use the AI Exit Decision Engine and AI LOI Analyzer as structured review aids, not substitutes for counsel. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 48 | Model earnout probability, seller control, measurement definitions, timing, disputes, and downside cases. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 49 | Track every re-trade and quantify the seller impact. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 50 | Maintain explicit minimum acceptable economics and walk-away conditions. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 51 | Have transaction counsel and tax advisors review actual LOI and structure terms before execution. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: LOI/structure meets seller thresholds or the owner explicitly chooses to negotiate further or walk away.

DILIGENCE — Control requests, findings, disclosure, exposure, and buyer leverage.

### Primary EXOS route: 11 — DUE DILIGENCE & DEAL PROTECTION; 07 — AI EXIT INTELLIGENCE

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 52 | Operate the Due Diligence Command Center with request owner, due date, status, and response control. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 53 | Maintain the data room and document version discipline. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 54 | Track diligence findings and estimate financial/legal/operational exposure. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 55 | Use the AI Deal Risk Register Generator to structure Risk / Probability / Financial Impact / Mitigation / Owner. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 56 | Escalate issues that could trigger price reductions, indemnity changes, special escrows, closing delays, or termination. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 57 | Coordinate management, legal, tax, accounting, HR, IT/cyber, insurance, customer, and operational diligence workstreams. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 58 | Track buyer responsiveness and transaction momentum throughout diligence. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: material findings are resolved, disclosed, mitigated, priced, or accepted; no unmanaged critical exposure remains.

CLOSE — Drive all conditions, documents, approvals, funds flow, and obligations to a funded closing.

### Primary EXOS route: 10 — TRANSACTION EXECUTION & DEAL CONTROL; 13 — CLOSING & TRANSITION

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 59 | Use the Deal Momentum / Probability-to-Close Score to monitor live closing certainty. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 60 | Track financing, legal documentation, third-party consents, regulatory approvals, management matters, and remaining diligence conditions. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 61 | Maintain the Exit Advisory Team Command Center and resolve advisor bottlenecks. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 62 | Complete the Closing Readiness Dashboard and Closing Conditions Tracker. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 63 | Validate purchase-price mechanics, working-capital adjustment, escrow, indemnity, rollover, seller note, earnout, and funds-flow details. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 64 | Confirm signatures, wire instructions, closing deliverables, transition obligations, communications, and Day 1 plan. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 65 | Do not treat the transaction as complete until funds and required closing confirmations are received. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: all material closing conditions and funds-flow requirements are satisfied and the transaction funds.

TRANSITION — Protect the owner, wealth, obligations, relationships, identity, and legacy after closing.

### Primary EXOS route: 13 — CLOSING & TRANSITION; 14 — POST-EXIT WEALTH, LIFE & LEGACY

| # | ACTION / MILESTONE | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 66 | Execute the agreed employee, customer, supplier, family, and stakeholder communication plan. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 67 | Track seller transition services, employment/consulting obligations, earnout requirements, rollover obligations, indemnity matters, and post-close covenants. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 68 | Coordinate tax payments, estimated taxes, estate actions, liquidity planning, insurance, and wealth deployment with qualified advisors. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 69 | Implement the post-exit Wealth Deployment Plan only after professional review. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 70 | Complete the Founder Identity Transition Workbook and establish a healthy post-exit operating rhythm. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 71 | Track earnout and contingent-payment performance and preserve supporting evidence. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 72 | Review legacy, philanthropy, family governance, succession, and long-term purpose priorities. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |
| 73 | Complete a formal post-exit review and close remaining EXOS obligations. |  |  | ☐ Not Started ☐ In Progress ☐ Complete |

Gate: post-close obligations, wealth/tax actions, identity transition, and legacy priorities are actively managed.

MASTER PROGRESS SUMMARY

| STAGE | STATUS | LARGEST OPEN ISSUE | OWNER | NEXT REVIEW |
| --- | --- | --- | --- | --- |
| ASSESS | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |
| VALUE | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |
| IMPROVE | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |
| PREPARE | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |
| MARKET | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |
| QUALIFY | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |
| NEGOTIATE | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |
| DILIGENCE | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |
| CLOSE | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |
| TRANSITION | ☐ Not Started ☐ Active ☐ Gate Complete |  |  |  |

EXECUTIVE REVIEW QUESTIONS

What is the single most important decision the owner must make now?

What is the largest current threat to value, timing, leverage, or closing?

Which ORANGE or RED condition requires management intervention?

What changed since the last review?

Which assumption needs advisor validation?

What is the next EXOS tool or stage gate that should be opened?

PROFESSIONAL USE NOTICE

EXOS is an educational planning and operating system. It does not substitute for an attorney, CPA, tax advisor, investment advisor, valuation professional, investment banker, M&A advisor, estate attorney, insurance professional, lender, or other qualified professional. Material legal, tax, accounting, valuation, securities, financing, estate, investment, or transaction decisions should be reviewed by the appropriate qualified professionals.